## Master Summary
Test Case Generation Summary
Generation Date: 2026-07-25 23:05 ¦ Generated by PS AI QA Assistant v2.5 | Source: Confluence 'Epic 08 - Data Migration' (5046665221); Canon_DM_001..009 (Jira keys TBD)
Feature / Source | Source Reference | Requirements | Acceptance Criteria | Test Cases | AC Coverage %
DM001 Migrate Service Contracts | CMCCBNP-8001 | 1 | 5 | 9 | 100%
DM002 Migrate Install Assets | CMCCBNP-8002 | 1 | 5 | 8 | 100%
DM003 Migrate Attachments | CMCCBNP-8003 | 1 | 3 | 5 | 100%
DM004 Historical Archive | CMCCBNP-8004 | 1 | 4 | 6 | 100%
DM005 Cancellation Integration | CMCCBNP-8005 | 1 | 5 | 8 | 100%
DM006 Master Agreement Hier | CMCCBNP-8006 | 1 | 3 | 5 | 100%
DM007 Field Mapping Validation | CMCCBNP-8007 | 1 | 4 | 6 | 100%
DM008 Reconnect FSL Objects | CMCCBNP-8008 | 1 | 4 | 6 | 100%
DM009 Legacy Product Mapping | CMCCBNP-8009 | 1 | 3 | 5 | 100%
TOTAL |  | 9 | 36 | 58 | 100%

## DM001 Migrate Service Contracts
Canon_DM_001 Migrate Active & Inactive Service Contracts to Conga Agreements
Source: Confluence 'Epic 08 - Data Migration' (5046665221) > Canon_DM_001 (Jira key TBD; ID placeholder CMCCBNP-8001)
Test Case ID | Requirement Title | Test Case Title | Pre-Conditions | Step# | Test Step | Expected Result | Priority
CMCCBNP-8001-TC-001 | Canon_DM_001 Migrate Active & Inactive Service Contracts to Conga Agreements | [Positive] Active and Inactive contracts with end date after cutover are created as Conga Agreements | 1. User is logged in with the CPQ Admin role. 2. User has the permissions required to perform this migration/validation activity. 3. A Salesforce source set exists with contracts in Active and Inactive status whose end date is after the cutover date. 4. The migration job and cutover date are configured. | 1 | Identify the eligible source contracts (status Active/Inactive, end date > cutover). | The eligible source contracts are identified in Salesforce. | High
|  |  |  | 2 | Execute the service-contract migration job. | The migration job runs to completion for the eligible set.
|  |  |  | 3 | Open the migrated records in Conga. | The Conga Agreements area is displayed.
|  |  |  | 4 | Confirm a Conga Agreement exists for each eligible source contract. | • Each eligible Active/Inactive source contract is created as a Conga Agreement. • The migrated Agreement count matches the eligible source count. • No eligible contract is omitted.
CMCCBNP-8001-TC-002 | Canon_DM_001 Migrate Active & Inactive Service Contracts to Conga Agreements | [Positive] Salesforce-to-Conga field mapping is completed and validated | 1. User is logged in with the CPQ Admin role. 2. User has the permissions required to perform this migration/validation activity. 3. A migrated Conga Agreement and its source Salesforce contract are available for comparison. 4. The field mapping specification is defined. | 1 | Open the source Salesforce contract and note the mapped header field values. | The source contract field values are recorded. | High
|  |  |  | 2 | Open the corresponding migrated Conga Agreement. | The migrated Agreement is displayed.
|  |  |  | 3 | Compare each mapped header field against the source. | Each mapped Conga field matches the source Salesforce value.
|  |  |  | 4 | Confirm the mapping across the sampled fields. | • The Salesforce-to-Conga field mapping is applied for all documented fields. • Each mapped field value matches its source. • No mapped field is left blank where the source had a value.
CMCCBNP-8001-TC-003 | Canon_DM_001 Migrate Active & Inactive Service Contracts to Conga Agreements | [Positive] Legacy contract number is stored on the Conga Agreement for traceability | 1. User is logged in with the CPQ Admin role. 2. User has the permissions required to perform this migration/validation activity. 3. A migrated Conga Agreement originates from a Salesforce contract with a known legacy contract number. | 1 | Note the legacy contract number on the source Salesforce contract. | The legacy contract number is recorded. | High
|  |  |  | 2 | Open the migrated Conga Agreement. | The migrated Agreement is displayed.
|  |  |  | 3 | Locate the legacy contract number field on the Agreement. | The legacy contract number field is populated.
|  |  |  | 4 | Compare the stored value to the source. | • The legacy contract number is stored on the Conga Agreement. • The stored value matches the source Salesforce contract number. • The number supports traceability back to the legacy contract.
CMCCBNP-8001-TC-004 | Canon_DM_001 Migrate Active & Inactive Service Contracts to Conga Agreements | [Positive] Contract line items are migrated with coverage type, pricing, duration, and entitlements intact | 1. User is logged in with the CPQ Admin role. 2. User has the permissions required to perform this migration/validation activity. 3. A migrated Conga Agreement has line items sourced from a Salesforce contract with coverage, pricing, duration, and entitlement details. | 1 | Note the source contract line-item details (coverage type, pricing, duration, entitlements). | The source line-item details are recorded. | High
|  |  |  | 2 | Open the migrated Conga Agreement's line items. | The Agreement line items are displayed.
|  |  |  | 3 | Compare coverage type and pricing per line item. | Coverage type and pricing match the source per line.
|  |  |  | 4 | Compare duration and entitlement details per line item. | • Line items are migrated with coverage type, pricing, duration, and entitlement details intact. • Each migrated line item matches its source line. • No line-item detail is missing or altered.
CMCCBNP-8001-TC-005 | Canon_DM_001 Migrate Active & Inactive Service Contracts to Conga Agreements | [Positive] Migrated contracts retain existing product structure without bundle restructuring | 1. User is logged in with the CPQ Admin role. 2. User has the permissions required to perform this migration/validation activity. 3. A migrated Conga Agreement originates from a Salesforce contract with a defined product/bundle structure. | 1 | Note the product/bundle structure on the source contract. | The source product structure is recorded. | Medium
|  |  |  | 2 | Open the migrated Conga Agreement's product structure. | The Agreement product structure is displayed.
|  |  |  | 3 | Compare the migrated structure to the source. | • The migrated contract retains the existing product structure. • No bundle restructuring is applied during migration. • The product relationships match the source contract.
CMCCBNP-8001-TC-006 | Canon_DM_001 Migrate Active & Inactive Service Contracts to Conga Agreements | [Negative] A contract with end date on or before the cutover date is excluded from migration | 1. User is logged in with the CPQ Admin role. 2. User has the permissions required to perform this migration/validation activity. 3. A Salesforce contract has status Active/Inactive but an end date on or before the cutover date. | 1 | Identify the source contract whose end date is on/before the cutover date. | The ineligible-by-date contract is identified. | High
|  |  |  | 2 | Execute the migration job. | The migration job runs.
|  |  |  | 3 | Search Conga for an Agreement created from that contract. | • No Conga Agreement is created for the contract whose end date is not after the cutover. • The date-ineligible contract is excluded from migration. • Only contracts with end date greater than the cutover are migrated.
CMCCBNP-8001-TC-007 | Canon_DM_001 Migrate Active & Inactive Service Contracts to Conga Agreements | [Negative] A contract with a status other than Active or Inactive is excluded | 1. User is logged in with the CPQ Admin role. 2. User has the permissions required to perform this migration/validation activity. 3. A Salesforce contract has a status other than Active or Inactive (e.g. Draft) with end date after cutover. | 1 | Identify the source contract with a non-eligible status. | The status-ineligible contract is identified. | High
|  |  |  | 2 | Execute the migration job. | The migration job runs.
|  |  |  | 3 | Search Conga for an Agreement created from that contract. | • No Conga Agreement is created for the status-ineligible contract. • Only Active and Inactive contracts are migrated. • The excluded contract remains only in Salesforce.
CMCCBNP-8001-TC-008 | Canon_DM_001 Migrate Active & Inactive Service Contracts to Conga Agreements | [Edge Case] Migrated line-item counts and values reconcile against the source contract | 1. User is logged in with the CPQ Admin role. 2. User has the permissions required to perform this migration/validation activity. 3. A migrated Conga Agreement and its source contract are available for reconciliation. | 1 | Count the line items on the source Salesforce contract. | The source line-item count is recorded. | Medium
|  |  |  | 2 | Count the line items on the migrated Conga Agreement. | The migrated line-item count is recorded.
|  |  |  | 3 | Compare the two counts and spot-check values. | • The migrated line-item count equals the source line-item count. • Spot-checked coverage/pricing/duration values reconcile to the source. • No line item is added, dropped, or altered in migration.
CMCCBNP-8001-TC-009 | Canon_DM_001 Migrate Active & Inactive Service Contracts to Conga Agreements | [Edge Case] A contract with end date exactly at the cutover boundary is handled per the rule | 1. User is logged in with the CPQ Admin role. 2. User has the permissions required to perform this migration/validation activity. 3. A Salesforce contract has an end date exactly equal to the cutover date (boundary case). | 1 | Identify the contract whose end date equals the cutover date. | The boundary contract is identified. | Medium
|  |  |  | 2 | Execute the migration job. | The migration job runs.
|  |  |  | 3 | Check whether a Conga Agreement was created for the boundary contract. | • The boundary contract is handled per the 'end date greater than cutover' rule (equal-to is not greater-than, so excluded). • The boundary treatment is consistent and deterministic. • The exact-boundary handling is confirmed against the stated rule (wording TBC).

## DM002 Migrate Install Assets
Canon_DM_002 Migrate Physical Install Base Assets to Conga Assets
Source: Confluence 'Epic 08 - Data Migration' (5046665221) > Canon_DM_002 (Jira key TBD; ID placeholder CMCCBNP-8002)
Test Case ID | Requirement Title | Test Case Title | Pre-Conditions | Step# | Test Step | Expected Result | Priority
CMCCBNP-8002-TC-001 | Canon_DM_002 Migrate Physical Install Base Assets to Conga Assets | [Positive] Assets with status Installed, Installed and MU, or Created are migrated to Conga Assets | 1. User is logged in with the CPQ Admin role. 2. User has the permissions required to perform this migration/validation activity. 3. A Salesforce source set contains assets in status Installed, Installed and MU, and Created. 4. The asset migration job is configured. | 1 | Identify the eligible source assets (Installed / Installed and MU / Created). | The eligible source assets are identified. | High
|  |  |  | 2 | Execute the asset migration job. | The migration job runs to completion for the eligible set.
|  |  |  | 3 | Open the migrated records in Conga Assets. | The Conga Assets area is displayed.
|  |  |  | 4 | Confirm a Conga Asset exists for each eligible source asset. | • Each eligible Installed/Installed and MU/Created asset is migrated to Conga Assets. • The migrated asset count matches the eligible source count. • No eligible asset is omitted.
CMCCBNP-8002-TC-002 | Canon_DM_002 Migrate Physical Install Base Assets to Conga Assets | [Positive] Parent-child asset hierarchy is preserved | 1. User is logged in with the CPQ Admin role. 2. User has the permissions required to perform this migration/validation activity. 3. A migrated set includes a parent asset with child assets from the source. | 1 | Note the parent-child hierarchy on the source assets. | The source hierarchy is recorded. | High
|  |  |  | 2 | Open the migrated parent asset in Conga. | The migrated parent asset is displayed.
|  |  |  | 3 | Review the child assets under the migrated parent. | The child assets are linked under the parent in Conga.
|  |  |  | 4 | Compare the migrated hierarchy to the source. | • The parent-child asset hierarchy is preserved in Conga. • Each child asset references its correct parent. • No hierarchy relationship is lost or flattened.
CMCCBNP-8002-TC-003 | Canon_DM_002 Migrate Physical Install Base Assets to Conga Assets | [Positive] Each asset is linked to the corresponding equipment site account | 1. User is logged in with the CPQ Admin role. 2. User has the permissions required to perform this migration/validation activity. 3. Migrated assets originate from source assets that carried an equipment site account. | 1 | Note the equipment site account on a source asset. | The source equipment site account is recorded. | High
|  |  |  | 2 | Open the corresponding migrated Conga Asset. | The migrated asset is displayed.
|  |  |  | 3 | Confirm the linked equipment site account is valid for the asset. | The linked equipment site account is a valid account for the asset.
|  |  |  | 4 | Review the equipment site account link on the asset. | • The migrated asset is linked to the corresponding equipment site account. • The linked account matches the source asset's site. • No asset is left without its equipment site linkage where the source had one.
CMCCBNP-8002-TC-004 | Canon_DM_002 Migrate Physical Install Base Assets to Conga Assets | [Positive] Custom fields (software version, usage tracking, serial number) are mapped and populated | 1. User is logged in with the CPQ Admin role. 2. User has the permissions required to perform this migration/validation activity. 3. Source assets carry custom fields including software version, usage tracking, and serial number. | 1 | Note the custom field values on a source asset. | The source custom field values are recorded. | High
|  |  |  | 2 | Open the corresponding migrated Conga Asset. | The migrated asset is displayed.
|  |  |  | 3 | Review the software version and serial number fields. | The software version and serial number are populated and match the source.
|  |  |  | 4 | Review the usage tracking field. | • The custom fields (software version, usage tracking, serial number) are mapped and populated. • Each custom field value matches the source asset. • No mapped custom field is left blank where the source had a value.
CMCCBNP-8002-TC-005 | Canon_DM_002 Migrate Physical Install Base Assets to Conga Assets | [Negative] De-installed assets are excluded from migration and remain in Salesforce | 1. User is logged in with the CPQ Admin role. 2. User has the permissions required to perform this migration/validation activity. 3. A source asset has a De-installed status. | 1 | Identify the De-installed source asset. | The De-installed asset is identified in Salesforce. | High
|  |  |  | 2 | Execute the asset migration job. | The migration job runs.
|  |  |  | 3 | Search Conga Assets for the De-installed asset. | No Conga Asset is created for the De-installed asset.
|  |  |  | 4 | Confirm the De-installed asset remains accessible in Salesforce. | • The De-installed asset is excluded from migration. • No Conga Asset is created for it. • The De-installed asset remains accessible in Salesforce.
CMCCBNP-8002-TC-006 | Canon_DM_002 Migrate Physical Install Base Assets to Conga Assets | [Negative] An asset with a non-eligible status is not migrated | 1. User is logged in with the CPQ Admin role. 2. User has the permissions required to perform this migration/validation activity. 3. A source asset has a status that is not Installed, Installed and MU, or Created (and not De-installed). | 1 | Identify the source asset with a non-eligible status. | The status-ineligible asset is identified. | Medium
|  |  |  | 2 | Execute the asset migration job. | The migration job runs.
|  |  |  | 3 | Search Conga Assets for that asset. | • No Conga Asset is created for the non-eligible-status asset. • Only Installed/Installed and MU/Created assets are migrated. • The excluded asset remains in Salesforce.
CMCCBNP-8002-TC-007 | Canon_DM_002 Migrate Physical Install Base Assets to Conga Assets | [Edge Case] A deep multi-level asset hierarchy is preserved end to end | 1. User is logged in with the CPQ Admin role. 2. User has the permissions required to perform this migration/validation activity. 3. A source asset tree has multiple hierarchy levels (parent, child, grandchild). | 1 | Note the multi-level hierarchy on the source assets. | The multi-level source hierarchy is recorded. | Medium
|  |  |  | 2 | Open the migrated top-level asset in Conga. | The migrated top-level asset is displayed.
|  |  |  | 3 | Traverse the hierarchy down to the deepest level. | Each level links correctly to its parent through to the deepest node.
|  |  |  | 4 | Compare the full migrated tree to the source. | • The multi-level parent-child hierarchy is preserved end to end. • Each node references its correct parent at every level. • No level is flattened or reparented incorrectly.
CMCCBNP-8002-TC-008 | Canon_DM_002 Migrate Physical Install Base Assets to Conga Assets | [Edge Case] A source custom field with a null value migrates without inventing a value | 1. User is logged in with the CPQ Admin role. 2. User has the permissions required to perform this migration/validation activity. 3. A source asset has a mapped custom field (e.g. usage tracking) with a null/empty value. | 1 | Note the null custom field on the source asset. | The null custom field is recorded. | Low
|  |  |  | 2 | Open the corresponding migrated Conga Asset. | The migrated asset is displayed.
|  |  |  | 3 | Review the same custom field on the migrated asset. | • The custom field remains null/empty on the migrated asset (no invented value). • The migration does not populate a value the source did not have. • Other populated fields on the asset are unaffected.

## DM003 Migrate Attachments
Canon_DM_003 Migrate Document Attachments from Service Contracts
Source: Confluence 'Epic 08 - Data Migration' (5046665221) > Canon_DM_003 (Jira key TBD; ID placeholder CMCCBNP-8003)
Test Case ID | Requirement Title | Test Case Title | Pre-Conditions | Step# | Test Step | Expected Result | Priority
CMCCBNP-8003-TC-001 | Canon_DM_003 Migrate Document Attachments from Service Contracts | [Positive] File attachments on migrated contracts are transferred to the corresponding Conga Agreement | 1. User is logged in with the CLM Admin role. 2. User has the permissions required to perform this migration/validation activity. 3. A source service contract has one or more file attachments and has been migrated to a Conga Agreement. | 1 | Note the attachments on the source service contract. | The source attachments (names/count) are recorded. | High
|  |  |  | 2 | Execute the attachment migration for the contract. | The attachment migration runs for the contract.
|  |  |  | 3 | Open the corresponding Conga Agreement's files/attachments section. | The Agreement files section is displayed.
|  |  |  | 4 | Confirm each source attachment is present on the Agreement. | • All source contract attachments are transferred to the corresponding Conga Agreement. • Each attachment appears on the Agreement record. • No attachment is missing from the target.
CMCCBNP-8003-TC-002 | Canon_DM_003 Migrate Document Attachments from Service Contracts | [Positive] Attachments on parent-level assets are migrated where applicable | 1. User is logged in with the CLM Admin role. 2. User has the permissions required to perform this migration/validation activity. 3. A source parent-level asset carries attachments that are in scope for migration. | 1 | Note the attachments on the source parent-level asset. | The parent-asset attachments are recorded. | Medium
|  |  |  | 2 | Execute the attachment migration for the parent asset. | The attachment migration runs for the parent asset.
|  |  |  | 3 | Open the corresponding migrated Conga Asset's files section. | The migrated asset files section is displayed.
|  |  |  | 4 | Confirm the parent-asset attachments are present. | • Attachments on parent-level assets are migrated where applicable. • Each in-scope parent-asset attachment appears on the migrated asset. • No applicable attachment is omitted.
CMCCBNP-8003-TC-003 | Canon_DM_003 Migrate Document Attachments from Service Contracts | [Positive] File integrity is validated via file count and size reconciliation | 1. User is logged in with the CLM Admin role. 2. User has the permissions required to perform this migration/validation activity. 3. Attachments have been migrated for a set of contracts and a reconciliation step is available. | 1 | Record the source file count and total size for the set. | The source file count and size are recorded. | High
|  |  |  | 2 | Record the target file count and total size after migration. | The target file count and size are recorded.
|  |  |  | 3 | Run the file integrity reconciliation. | The reconciliation compares source and target counts and sizes.
|  |  |  | 4 | Review the reconciliation result. | • The file count reconciles between source and target. • The total file size reconciles between source and target. • File integrity is validated with no discrepancy.
CMCCBNP-8003-TC-004 | Canon_DM_003 Migrate Document Attachments from Service Contracts | [Negative] A file count or size mismatch is detected by reconciliation | 1. User is logged in with the CLM Admin role. 2. User has the permissions required to perform this migration/validation activity. 3. An attachment migration produced a count or size discrepancy (test scenario). | 1 | Record the source file count and size. | The source values are recorded. | High
|  |  |  | 2 | Record the target file count and size showing a discrepancy. | The target values differ from the source.
|  |  |  | 3 | Run the file integrity reconciliation. | • The reconciliation detects and reports the file count/size mismatch. • The discrepancy is surfaced for correction (wording TBC). • The migration is not treated as integrity-validated while a mismatch exists.
CMCCBNP-8003-TC-005 | Canon_DM_003 Migrate Document Attachments from Service Contracts | [Edge Case] A contract with no attachments migrates cleanly with an empty file set | 1. User is logged in with the CLM Admin role. 2. User has the permissions required to perform this migration/validation activity. 3. A source service contract has zero attachments and has been migrated. | 1 | Confirm the source contract has no attachments. | The source contract shows zero attachments. | Low
|  |  |  | 2 | Execute the attachment migration for the contract. | The attachment migration runs.
|  |  |  | 3 | Open the corresponding Conga Agreement's files section. | • The Agreement is migrated with an empty attachment set (no error). • No spurious/placeholder attachment is created. • The zero-attachment case reconciles to a count of zero.

## DM004 Historical Archive
Canon_DM_004 Create Historical Archive for Expired & Terminated Contracts
Source: Confluence 'Epic 08 - Data Migration' (5046665221) > Canon_DM_004 (Jira key TBD; ID placeholder CMCCBNP-8004)
Test Case ID | Requirement Title | Test Case Title | Pre-Conditions | Step# | Test Step | Expected Result | Priority
CMCCBNP-8004-TC-001 | Canon_DM_004 Create Historical Archive for Expired & Terminated Contracts | [Positive] Custom archive object stores header and line-item details for expired and terminated contracts | 1. User is logged in with the System Admin role. 2. User has the permissions required to perform this migration/validation activity. 3. Expired and terminated service contracts exist in the source and the archive object is configured. | 1 | Identify the expired and terminated source contracts. | The expired/terminated contracts are identified. | High
|  |  |  | 2 | Run the archive process to populate the custom object. | The archive process populates the custom Salesforce object.
|  |  |  | 3 | Open an archived record in the custom object. | The archived record is displayed.
|  |  |  | 4 | Review the header and line-item details on the archived record. | • The custom archive object stores header and line-item details for each expired/terminated contract. • Each archived record includes both header and line-item data. • Every expired/terminated contract is represented in the archive.
CMCCBNP-8004-TC-002 | Canon_DM_004 Create Historical Archive for Expired & Terminated Contracts | [Positive] Internal notes and comments are included in the archive | 1. User is logged in with the System Admin role. 2. User has the permissions required to perform this migration/validation activity. 3. An expired/terminated source contract has internal notes and comments and has been archived. | 1 | Note the internal notes and comments on the source contract. | The source notes/comments are recorded. | Medium
|  |  |  | 2 | Open the corresponding archived record. | The archived record is displayed.
|  |  |  | 3 | Review the notes and comments captured in the archive. | • Internal notes and comments are included in the archived record. • The archived notes/comments match the source. • No note or comment is dropped in archiving.
CMCCBNP-8004-TC-003 | Canon_DM_004 Create Historical Archive for Expired & Terminated Contracts | [Positive] Archived records are searchable by account, asset, and contract number | 1. User is logged in with the Operations User role. 2. User has the permissions required to perform this migration/validation activity. 3. Archived records exist in the custom object with account, asset, and contract-number references. | 1 | Open the archive search interface. | The archive search interface is displayed. | High
|  |  |  | 2 | Search archived records by account. | Records for the account are returned.
|  |  |  | 3 | Search archived records by asset. | Records for the asset are returned.
|  |  |  | 4 | Search archived records by contract number. | • Archived records are searchable by account, asset, and contract number. • Each search returns the correct archived records. • The search keys resolve to the intended records.
CMCCBNP-8004-TC-004 | Canon_DM_004 Create Historical Archive for Expired & Terminated Contracts | [Negative] Operations users have read-only access to the archive (no create/edit/delete) | 1. User is logged in with the Operations User role. 2. User has the permissions required to perform this migration/validation activity. 3. Archived records exist and the Operations User has read-only access configured. | 1 | Open an archived record as the Operations User. | The archived record is displayed in read mode. | High
|  |  |  | 2 | Attempt to edit a field on the archived record. | No edit is permitted on the archived record.
|  |  |  | 3 | Attempt to create or delete an archived record. | • The Operations User can view archived records but cannot edit, create, or delete them. • No transactional capability is available on the archive for this role. • The read-only access is enforced (wording TBC).
CMCCBNP-8004-TC-005 | Canon_DM_004 Create Historical Archive for Expired & Terminated Contracts | [Negative] A contract that is not expired or terminated is not archived | 1. User is logged in with the System Admin role. 2. User has the permissions required to perform this migration/validation activity. 3. A source contract is Active/Inactive (not expired or terminated). | 1 | Identify a source contract that is not expired or terminated. | The non-eligible contract is identified. | Medium
|  |  |  | 2 | Run the archive process. | The archive process runs.
|  |  |  | 3 | Search the archive for that contract. | • No archive record is created for the non-expired/terminated contract. • Only expired and terminated contracts are archived. • The active contract is excluded from the archive.
CMCCBNP-8004-TC-006 | Canon_DM_004 Create Historical Archive for Expired & Terminated Contracts | [Edge Case] Archive search returns the correct record for each individual search key | 1. User is logged in with the Operations User role. 2. User has the permissions required to perform this migration/validation activity. 3. An archived record is retrievable by its account, asset, and contract number. | 1 | Search the archive by the exact contract number. | The archive returns the matching record for the contract number. | Medium
|  |  |  | 2 | Search the archive by the associated account. | The archive returns records for that account, including the target.
|  |  |  | 3 | Search the archive by the associated asset. | • Each individual search key (account, asset, contract number) returns the correct archived record. • No key returns an unrelated record for the exact match. • The record is consistently retrievable across all three keys.

## DM005 Cancellation Integration
Canon_DM_005 Enable Cancellation Integration for Legacy Contracts
Source: Confluence 'Epic 08 - Data Migration' (5046665221) > Canon_DM_005 (Jira key TBD; ID placeholder CMCCBNP-8005)
Test Case ID | Requirement Title | Test Case Title | Pre-Conditions | Step# | Test Step | Expected Result | Priority
CMCCBNP-8005-TC-001 | Canon_DM_005 Enable Cancellation Integration for Legacy Contracts | [Positive] Each migrated Conga Agreement stores the corresponding D365 contract number | 1. User is logged in with the System Admin role. 2. User has the permissions required to perform this migration/validation activity. 3. A migrated legacy Conga Agreement originates from a contract with a known D365 contract number. | 1 | Note the D365 contract number for the source legacy contract. | The D365 contract number is recorded. | High
|  |  |  | 2 | Open the migrated Conga Agreement. | The migrated Agreement is displayed.
|  |  |  | 3 | Locate the D365 contract number field on the Agreement. | The D365 contract number field is populated.
|  |  |  | 4 | Compare the stored value to the source. | • The migrated Conga Agreement stores the corresponding D365 contract number. • The stored value matches the source D365 reference. • The reference supports the cancellation integration.
CMCCBNP-8005-TC-002 | Canon_DM_005 Enable Cancellation Integration for Legacy Contracts | [Positive] A cancellation trigger sends an outbound cancellation message to D365 | 1. User is logged in with the Finance User role. 2. User has the permissions required to perform this migration/validation activity. 3. A migrated Conga Agreement with a D365 contract number is eligible for cancellation. 4. The outbound D365 integration is configured. | 1 | Open the migrated Conga Agreement. | The Agreement is displayed. | High
|  |  |  | 2 | Set the cancellation trigger (status change or checkbox). | The cancellation trigger is set on the Agreement.
|  |  |  | 3 | Confirm the cancellation. | The cancellation is confirmed.
|  |  |  | 4 | Review the outbound integration to D365. | • An outbound cancellation message is sent to D365 on the trigger. • The message references the correct D365 contract number. • The integration records the cancellation send (config TBC).
CMCCBNP-8005-TC-003 | Canon_DM_005 Enable Cancellation Integration for Legacy Contracts | [Positive] Pro-rated credit is calculated using contract line value and remaining term | 1. User is logged in with the Finance User role. 2. User has the permissions required to perform this migration/validation activity. 3. A migrated Agreement being cancelled has line values and a remaining term. | 1 | Open the Agreement being cancelled. | The Agreement is displayed with its line values and term. | High
|  |  |  | 2 | Note the contract line value and the remaining term. | The line value and remaining term are recorded.
|  |  |  | 3 | Trigger the pro-rated credit calculation. | The pro-rated credit is calculated.
|  |  |  | 4 | Review the calculated credit against the inputs. | • The pro-rated credit is calculated using the contract line value and remaining term. • The calculated credit is proportional to the remaining term. • The calculation is consistent with the line value inputs (value TBC).
CMCCBNP-8005-TC-004 | Canon_DM_005 Enable Cancellation Integration for Legacy Contracts | [Positive] The Conga Agreement status updates to Terminated upon cancellation | 1. User is logged in with the Finance User role. 2. User has the permissions required to perform this migration/validation activity. 3. A migrated Agreement is cancelled via the cancellation trigger. | 1 | Open the Agreement prior to cancellation. | The Agreement shows its pre-cancellation status. | High
|  |  |  | 2 | Execute the cancellation. | The cancellation is executed.
|  |  |  | 3 | Confirm the cancellation trigger was applied before checking status. | The cancellation trigger is recorded on the Agreement.
|  |  |  | 4 | Review the Agreement status after cancellation. | • The Conga Agreement status updates to Terminated upon cancellation. • The Status Category reflects the Terminated state. • The status change is recorded on the Agreement.
CMCCBNP-8005-TC-005 | Canon_DM_005 Enable Cancellation Integration for Legacy Contracts | [Positive] Asset entitlements are cleared when the contract is terminated | 1. User is logged in with the System Admin role. 2. User has the permissions required to perform this migration/validation activity. 3. A terminated migrated Agreement has associated asset entitlements. | 1 | Note the asset entitlements linked to the Agreement before termination. | The pre-termination entitlements are recorded. | High
|  |  |  | 2 | Terminate the Agreement via cancellation. | The Agreement is terminated.
|  |  |  | 3 | Confirm the Agreement is in Terminated status before checking entitlements. | The Agreement status is Terminated.
|  |  |  | 4 | Review the associated asset entitlements after termination. | • The asset entitlements are cleared when the contract is terminated. • The assets no longer show active entitlements from the terminated contract. • The entitlement clearance is consistent with the termination.
CMCCBNP-8005-TC-006 | Canon_DM_005 Enable Cancellation Integration for Legacy Contracts | [Negative] No cancellation message is sent to D365 when the trigger is not set | 1. User is logged in with the Finance User role. 2. User has the permissions required to perform this migration/validation activity. 3. A migrated Agreement has a D365 contract number but the cancellation trigger has not been set. | 1 | Open the migrated Agreement without setting the cancellation trigger. | The Agreement is displayed with the trigger unset. | Medium
|  |  |  | 2 | Confirm the cancellation trigger remains unset. | The status change/checkbox trigger is not set.
|  |  |  | 3 | Review the outbound integration to D365. | • No outbound cancellation message is sent to D365 while the trigger is unset. • The integration only fires on the cancellation trigger. • The Agreement status is not changed to Terminated.
CMCCBNP-8005-TC-007 | Canon_DM_005 Enable Cancellation Integration for Legacy Contracts | [Negative] A D365 cancellation integration failure is surfaced and not falsely marked complete | 1. User is logged in with the Finance User role. 2. User has the permissions required to perform this migration/validation activity. 3. A cancellation is triggered while the D365 outbound integration is failing (config TBC). | 1 | Set the cancellation trigger on the Agreement. | The cancellation trigger is set. | High
|  |  |  | 2 | Attempt to send the cancellation while the D365 integration is failing. | The outbound send is attempted against the failing integration.
|  |  |  | 3 | Review the integration outcome. | • The D365 cancellation integration failure is surfaced to the user/log (wording TBC). • The cancellation is not falsely marked as successfully communicated. • The send can be retried once the integration is restored.
CMCCBNP-8005-TC-008 | Canon_DM_005 Enable Cancellation Integration for Legacy Contracts | [Edge Case] Pro-rated credit at a near-zero remaining term | 1. User is logged in with the Finance User role. 2. User has the permissions required to perform this migration/validation activity. 3. A migrated Agreement is cancelled when the remaining term is at or near zero (boundary). | 1 | Open the Agreement whose remaining term is at/near zero. | The Agreement shows a near-zero remaining term. | Medium
|  |  |  | 2 | Trigger the pro-rated credit calculation. | The pro-rated credit is calculated for the near-zero term.
|  |  |  | 3 | Review the calculated credit at the boundary. | • The pro-rated credit at a near-zero remaining term is at/near zero (no negative or inflated value). • The boundary calculation is proportional to the remaining term. • The near-zero boundary is handled deterministically (value TBC).

## DM006 Master Agreement Hier
Canon_DM_006 Migrate Master Service Agreement Hierarchy
Source: Confluence 'Epic 08 - Data Migration' (5046665221) > Canon_DM_006 (Jira key TBD; ID placeholder CMCCBNP-8006)
Test Case ID | Requirement Title | Test Case Title | Pre-Conditions | Step# | Test Step | Expected Result | Priority
CMCCBNP-8006-TC-001 | Canon_DM_006 Migrate Master Service Agreement Hierarchy | [Positive] Master agreements are created with child agreements linked underneath | 1. User is logged in with the CPQ Admin role. 2. User has the permissions required to perform this migration/validation activity. 3. A source master service agreement with related child contracts is in scope for migration. | 1 | Note the master-and-child structure on the source. | The source master/child structure is recorded. | High
|  |  |  | 2 | Execute the master-agreement migration. | The migration creates the master and child Agreements.
|  |  |  | 3 | Open the migrated master Agreement in Conga. | The migrated master Agreement is displayed.
|  |  |  | 4 | Review the child agreements linked under the master. | • The master agreement is created in Conga with its child agreements linked underneath. • Each child agreement references the correct master. • The consolidated grouping is preserved.
CMCCBNP-8006-TC-002 | Canon_DM_006 Migrate Master Service Agreement Hierarchy | [Positive] A field allows entry of the master contract number for interim additions | 1. User is logged in with the CPQ Admin role. 2. User has the permissions required to perform this migration/validation activity. 3. A Conga Agreement supports a master contract number field for interim additions. | 1 | Open a Conga Agreement that needs a master contract number. | The Agreement is displayed. | Medium
|  |  |  | 2 | Enter the master contract number in the designated field. | The master contract number is accepted in the field.
|  |  |  | 3 | Save the Agreement. | • The master contract number can be entered on the Agreement for interim additions. • The entered number is retained after save. • The field supports linking interim additions to the master.
CMCCBNP-8006-TC-003 | Canon_DM_006 Migrate Master Service Agreement Hierarchy | [Positive] The master contract number flows through to D365 sales orders | 1. User is logged in with the Finance User role. 2. User has the permissions required to perform this migration/validation activity. 3. A Conga Agreement with a master contract number generates a D365 sales order via integration. | 1 | Open the Agreement carrying the master contract number. | The Agreement shows the master contract number. | High
|  |  |  | 2 | Trigger the flow that creates/updates the D365 sales order. | The D365 sales order integration runs.
|  |  |  | 3 | Confirm the Agreement carries the master contract number before the flow. | The master contract number is present on the Agreement.
|  |  |  | 4 | Review the master contract number on the resulting D365 sales order. | • The master contract number flows through to the D365 sales order. • The D365 sales order reflects the master contract number. • The number supports consolidated invoicing in D365 (config TBC).
CMCCBNP-8006-TC-004 | Canon_DM_006 Migrate Master Service Agreement Hierarchy | [Edge Case] A child agreement uses the legacy master contract number reference instead of a linked master | 1. User is logged in with the CPQ Admin role. 2. User has the permissions required to perform this migration/validation activity. 3. An individual agreement references a legacy master contract number rather than a migrated master record. | 1 | Open the individual migrated Agreement. | The Agreement is displayed. | Medium
|  |  |  | 2 | Review the legacy master contract number reference on the Agreement. | The legacy master contract number is present as a reference.
|  |  |  | 3 | Confirm the grouping is preserved via the reference. | • The individual agreement references the legacy master contract number where a linked master is not created. • The reference preserves the consolidated grouping context. • The alternative (reference vs linked master) is applied per the migration approach (config TBC).
CMCCBNP-8006-TC-005 | Canon_DM_006 Migrate Master Service Agreement Hierarchy | [Negative] The master contract number does not flow to D365 when it is absent on the Agreement | 1. User is logged in with the Finance User role. 2. User has the permissions required to perform this migration/validation activity. 3. A Conga Agreement has no master contract number populated. | 1 | Open the Agreement with no master contract number. | The Agreement shows an empty master contract number field. | Medium
|  |  |  | 2 | Trigger the D365 sales order flow. | The D365 sales order integration runs.
|  |  |  | 3 | Review the master contract number on the D365 sales order. | • No master contract number flows to the D365 sales order when it is absent on the Agreement. • The sales order does not carry an invented master number. • Consolidated invoicing grouping is not applied without a master number.

## DM007 Field Mapping Validation
Canon_DM_007 Complete Field Mapping and Data Quality Validation
Source: Confluence 'Epic 08 - Data Migration' (5046665221) > Canon_DM_007 (Jira key TBD; ID placeholder CMCCBNP-8007)
Test Case ID | Requirement Title | Test Case Title | Pre-Conditions | Step# | Test Step | Expected Result | Priority
CMCCBNP-8007-TC-001 | Canon_DM_007 Complete Field Mapping and Data Quality Validation | [Positive] All standard and custom fields on assets, contracts, and line items are documented | 1. User is logged in with the System Admin role. 2. User has the permissions required to perform this migration/validation activity. 3. The field-mapping documentation for Salesforce assets, contracts, and contract line items is prepared. | 1 | Open the field-mapping documentation. | The field-mapping documentation is displayed. | High
|  |  |  | 2 | Review the documented fields for Salesforce assets. | All standard and custom asset fields are documented.
|  |  |  | 3 | Review the documented fields for contracts and contract line items. | • All standard and custom fields on assets, contracts, and contract line items are documented. • No source field is left undocumented. • The documentation covers all three object types.
CMCCBNP-8007-TC-002 | Canon_DM_007 Complete Field Mapping and Data Quality Validation | [Positive] Each field is mapped to a Conga field or flagged as requiring a custom field | 1. User is logged in with the System Admin role. 2. User has the permissions required to perform this migration/validation activity. 3. The field-mapping documentation includes a target mapping per source field. | 1 | Open the field-mapping documentation. | The mapping documentation is displayed. | High
|  |  |  | 2 | Review the Conga target mapping for each source field. | Each field has a Conga target or a custom-field-required flag.
|  |  |  | 3 | Confirm no source field is left unmapped and unflagged. | • Each field is mapped to a Conga field or flagged as requiring a custom field. • No source field is left without a mapping decision. • The mapping is complete and reviewable.
CMCCBNP-8007-TC-003 | Canon_DM_007 Complete Field Mapping and Data Quality Validation | [Positive] Pre-migration data quality checks are performed for missing values and inconsistencies | 1. User is logged in with the System Admin role. 2. User has the permissions required to perform this migration/validation activity. 3. A pre-migration data quality check is available for the source dataset. | 1 | Run the pre-migration data quality check on the source dataset. | The data quality check executes over the source data. | High
|  |  |  | 2 | Review the check output for missing values. | The output lists records with missing required values.
|  |  |  | 3 | Review the check output for inconsistencies. | • Pre-migration data quality checks are performed for missing values and inconsistencies. • The check reports missing values and inconsistent records. • The results are available to remediate before migration.
CMCCBNP-8007-TC-004 | Canon_DM_007 Complete Field Mapping and Data Quality Validation | [Positive] A reconciliation report confirms record counts between source and target | 1. User is logged in with the System Admin role. 2. User has the permissions required to perform this migration/validation activity. 3. A migration run has completed and a reconciliation report is available. | 1 | Open the reconciliation report after the migration run. | The reconciliation report is displayed. | High
|  |  |  | 2 | Review the source record counts per object. | The source record counts are shown.
|  |  |  | 3 | Confirm the reconciliation report covers each migrated object. | The report lists source and target counts per object.
|  |  |  | 4 | Compare the target record counts to the source. | • The reconciliation report confirms record counts between source and target. • The target counts match the source counts per object. • Any discrepancy is highlighted for review.
CMCCBNP-8007-TC-005 | Canon_DM_007 Complete Field Mapping and Data Quality Validation | [Negative] The data quality check flags records with missing values or inconsistencies | 1. User is logged in with the System Admin role. 2. User has the permissions required to perform this migration/validation activity. 3. The source dataset contains records with missing required values and inconsistencies (test scenario). | 1 | Introduce/confirm records with missing values and inconsistencies in the source. | The problematic records are present in the source. | High
|  |  |  | 2 | Run the pre-migration data quality check. | The check executes over the source data.
|  |  |  | 3 | Review the flagged records. | • The data quality check flags the records with missing values and inconsistencies. • Each problematic record is reported with its issue (wording TBC). • Clean records are not incorrectly flagged.
CMCCBNP-8007-TC-006 | Canon_DM_007 Complete Field Mapping and Data Quality Validation | [Negative] The reconciliation report flags a record-count mismatch between source and target | 1. User is logged in with the System Admin role. 2. User has the permissions required to perform this migration/validation activity. 3. A migration run produced a record-count discrepancy between source and target (test scenario). | 1 | Run a migration that yields a source/target count discrepancy. | The migration completes with differing counts. | High
|  |  |  | 2 | Open the reconciliation report. | The reconciliation report is displayed.
|  |  |  | 3 | Review the reported counts. | • The reconciliation report flags the record-count mismatch between source and target. • The discrepancy is highlighted rather than hidden. • The migration is not treated as reconciled while a mismatch exists.

## DM008 Reconnect FSL Objects
Canon_DM_008 Reconnect Field Service Lightning Objects to Conga Assets
Source: Confluence 'Epic 08 - Data Migration' (5046665221) > Canon_DM_008 (Jira key TBD; ID placeholder CMCCBNP-8008)
Test Case ID | Requirement Title | Test Case Title | Pre-Conditions | Step# | Test Step | Expected Result | Priority
CMCCBNP-8008-TC-001 | Canon_DM_008 Reconnect Field Service Lightning Objects to Conga Assets | [Positive] Maintenance plans are linked to the corresponding Conga Assets | 1. User is logged in with the System Admin role. 2. User has the permissions required to perform this migration/validation activity. 3. Maintenance plans previously linked to Salesforce assets exist and Conga Assets have been migrated. | 1 | Identify a maintenance plan and its source asset. | The maintenance plan and source asset are identified. | High
|  |  |  | 2 | Run the FSL reconnection for maintenance plans. | The reconnection links the plan to the migrated Conga Asset.
|  |  |  | 3 | Open the maintenance plan. | The maintenance plan is displayed.
|  |  |  | 4 | Review the linked Conga Asset on the plan. | • The maintenance plan is linked to the corresponding Conga Asset. • The linked asset matches the plan's original asset. • No maintenance plan is left unlinked after reconnection.
CMCCBNP-8008-TC-002 | Canon_DM_008 Reconnect Field Service Lightning Objects to Conga Assets | [Positive] Cases, service appointments, and work orders reference Conga Asset records | 1. User is logged in with the System Admin role. 2. User has the permissions required to perform this migration/validation activity. 3. Cases, service appointments, and work orders that referenced Salesforce assets exist. | 1 | Open a case that references an asset. | The case is displayed. | High
|  |  |  | 2 | Review the asset reference on the case, service appointment, and work order. | The FSL objects reference the migrated Conga Asset.
|  |  |  | 3 | Confirm the references resolve to the correct Conga Asset. | • Cases, service appointments, and work orders reference the correct Conga Asset records where required. • Each reference resolves to the migrated asset. • No required reference is left pointing to a stale Salesforce asset.
CMCCBNP-8008-TC-003 | Canon_DM_008 Reconnect Field Service Lightning Objects to Conga Assets | [Positive] Field service discounting entitlements are functional against Conga Assets | 1. User is logged in with the Operations User role. 2. User has the permissions required to perform this migration/validation activity. 3. Field service discounting entitlements are configured against migrated Conga Assets. | 1 | Open a work order/case that should apply a field service discount entitlement. | The record is displayed against a Conga Asset. | High
|  |  |  | 2 | Apply the field service discount entitlement. | The entitlement is evaluated against the Conga Asset.
|  |  |  | 3 | Confirm the entitlement is defined against the migrated Conga Asset. | The entitlement references the Conga Asset, not the legacy asset.
|  |  |  | 4 | Review the applied discount. | • Entitlements for field service discounting are functional against Conga Assets. • The discount applies correctly based on the Conga Asset entitlement. • The entitlement resolves against the migrated asset, not the legacy one.
CMCCBNP-8008-TC-004 | Canon_DM_008 Reconnect Field Service Lightning Objects to Conga Assets | [Positive] Asset swap flow for serial-tracked part replacements works with Conga Assets | 1. User is logged in with the Operations User role. 2. User has the permissions required to perform this migration/validation activity. 3. A serial-tracked Conga Asset is eligible for a part swap/replacement. | 1 | Open the serial-tracked Conga Asset. | The asset is displayed with its serial-tracked part. | High
|  |  |  | 2 | Initiate the asset swap flow for the part replacement. | The asset swap flow starts against the Conga Asset.
|  |  |  | 3 | Complete the swap to the replacement part. | The replacement part is applied to the Conga Asset.
|  |  |  | 4 | Review the asset after the swap. | • The asset swap flow for serial-tracked part replacements works with Conga Assets. • The replacement part and its serial are reflected on the Conga Asset. • The swap history is retained on the asset.
CMCCBNP-8008-TC-005 | Canon_DM_008 Reconnect Field Service Lightning Objects to Conga Assets | [Negative] An FSL object left pointing to a legacy asset is detectable after reconnection | 1. User is logged in with the System Admin role. 2. User has the permissions required to perform this migration/validation activity. 3. An FSL object (e.g. a work order) still references a legacy Salesforce asset after reconnection (test scenario). | 1 | Open the FSL object that still references the legacy asset. | The FSL object shows a legacy asset reference. | Medium
|  |  |  | 2 | Run the post-reconnection validation. | The validation checks FSL references against Conga Assets.
|  |  |  | 3 | Review the validation output. | • The FSL object still pointing to a legacy asset is flagged by the validation. • The unreconnected reference is surfaced for correction (wording TBC). • Reconnection is not treated as complete while stale references remain.
CMCCBNP-8008-TC-006 | Canon_DM_008 Reconnect Field Service Lightning Objects to Conga Assets | [Edge Case] Asset swap preserves the entitlement linkage on the Conga Asset | 1. User is logged in with the Operations User role. 2. User has the permissions required to perform this migration/validation activity. 3. A serial-tracked Conga Asset with an active entitlement undergoes a part swap. | 1 | Note the entitlement on the Conga Asset before the swap. | The pre-swap entitlement is recorded. | Medium
|  |  |  | 2 | Perform the asset swap for the serial-tracked part. | The part swap is completed on the Conga Asset.
|  |  |  | 3 | Review the entitlement linkage after the swap. | • The entitlement linkage is preserved on the Conga Asset after the swap. • The swap does not break the asset's field-service entitlement. • Coverage continuity is maintained across the part replacement.

## DM009 Legacy Product Mapping
Canon_DM_009 Create Legacy-to-New Product Mapping for Renewal Transition
Source: Confluence 'Epic 08 - Data Migration' (5046665221) > Canon_DM_009 (Jira key TBD; ID placeholder CMCCBNP-8009)
Test Case ID | Requirement Title | Test Case Title | Pre-Conditions | Step# | Test Step | Expected Result | Priority
CMCCBNP-8009-TC-001 | Canon_DM_009 Create Legacy-to-New Product Mapping for Renewal Transition | [Positive] A mapping table links each legacy service/warranty product to its Conga equivalent | 1. User is logged in with the CPQ Admin role. 2. User has the permissions required to perform this migration/validation activity. 3. Legacy Salesforce CPQ warranty/service products and new Conga CPQ products exist. 4. The mapping table is configured. | 1 | Open the legacy-to-new product mapping table. | The mapping table is displayed. | High
|  |  |  | 2 | Review the mapping for a legacy service product. | The legacy service product maps to its Conga equivalent.
|  |  |  | 3 | Review the mapping for a legacy warranty product. | The legacy warranty product maps to its Conga equivalent.
|  |  |  | 4 | Confirm every legacy product has a mapping entry. | • The mapping table links each legacy service/warranty product to its Conga equivalent. • Each legacy product resolves to exactly one Conga product. • No in-scope legacy product is missing from the mapping.
CMCCBNP-8009-TC-002 | Canon_DM_009 Create Legacy-to-New Product Mapping for Renewal Transition | [Positive] The mapping is accessible to operations users during renewal quoting | 1. User is logged in with the Operations User role. 2. User has the permissions required to perform this migration/validation activity. 3. The product mapping is available and a renewal quote is being created for a migrated contract. | 1 | Start a renewal quote for a migrated contract. | The renewal quote is initiated. | High
|  |  |  | 2 | Access the legacy-to-new product mapping during quoting. | The mapping is accessible within the renewal quoting flow.
|  |  |  | 3 | Use the mapping to select the Conga equivalent for a legacy product. | • The mapping is accessible to operations users during renewal quoting. • The correct Conga product can be selected via the mapping. • The renewal quote uses the new product structure.
CMCCBNP-8009-TC-003 | Canon_DM_009 Create Legacy-to-New Product Mapping for Renewal Transition | [Positive] The mapping is validated through a test renewal in the sandbox environment | 1. User is logged in with the CPQ Admin role. 2. User has the permissions required to perform this migration/validation activity. 3. A sandbox environment with the mapping and a migrated contract is available for a test renewal. | 1 | Open the sandbox environment. | The sandbox environment is displayed. | High
|  |  |  | 2 | Perform a test renewal of a migrated contract using the mapping. | The test renewal uses the legacy-to-new mapping.
|  |  |  | 3 | Review the renewed quote's product structure. | The renewed quote uses the mapped Conga products.
|  |  |  | 4 | Confirm the test renewal completes successfully. | • The mapping is validated through a successful test renewal in the sandbox. • The renewed products match the mapped Conga equivalents. • The test confirms the mapping supports renewal.
CMCCBNP-8009-TC-004 | Canon_DM_009 Create Legacy-to-New Product Mapping for Renewal Transition | [Negative] A legacy product with no Conga mapping is flagged during renewal | 1. User is logged in with the Operations User role. 2. User has the permissions required to perform this migration/validation activity. 3. A legacy product on a migrated contract has no entry in the mapping table. | 1 | Start a renewal quote for a contract containing an unmapped legacy product. | The renewal quote is initiated. | Medium
|  |  |  | 2 | Attempt to select the Conga equivalent for the unmapped legacy product. | No Conga equivalent is available for the unmapped product.
|  |  |  | 3 | Review the outcome. | • The legacy product with no Conga mapping is flagged during renewal. • A message indicates the product mapping is missing (wording TBC). • The renewal cannot proceed with an unmapped product until the mapping is added.
CMCCBNP-8009-TC-005 | Canon_DM_009 Create Legacy-to-New Product Mapping for Renewal Transition | [Edge Case] The mapping presents the correct Conga equivalent when a legacy product maps to a restructured product | 1. User is logged in with the Operations User role. 2. User has the permissions required to perform this migration/validation activity. 3. A legacy product maps to a Conga product with a different (restructured) configuration. | 1 | Start a renewal quote involving the restructured-product legacy item. | The renewal quote is initiated. | Low
|  |  |  | 2 | Use the mapping to resolve the legacy item to its Conga equivalent. | The mapping resolves to the restructured Conga product.
|  |  |  | 3 | Review the resulting product configuration on the quote. | • The mapping presents the correct Conga equivalent even when the target is restructured. • The renewal quote reflects the new product configuration. • The restructured mapping is applied consistently (config TBC).